## Gantt Chart
YCS Gantt Chart
TASK TITLE | TASK OWNER | START DATE | DUE DATE | Duration (Days) | PCT OF TASK COMPLETE
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
User Requirements
User must be able to create a profile. | Nick | 2019-02-25 | 2019-03-11 | 16 | 75% | bar: WEEK 1 M to WEEK 1 F; WEEK 2 F to WEEK 3 M; WEEK 4 M to WEEK 4 F
User must be able to modify an existing profile, given that they provide the correct credentials. | Nick | 2019-03-25 | 2019-04-02 | 7 | 25% | bar: WEEK 2 F; WEEK 4 M to WEEK 4 F; WEEK 5 T to WEEK 6 F
User must be able to log into the system if they provide a correct set of credentials | Nick | 2019-03-11 | 2019-03-25 | 14 | 75% | bar: WEEK 2 F; WEEK 3 T to WEEK 5 M
User must be able to take a quiz outlining their preferences for living conditions | Michael | 2019-03-11 | 2019-03-22 | 11 | 100% | bar: WEEK 2 F to WEEK 4 F
User must be able to modify the results of a previously taken quiz | Andrew | 2019-03-18 | 2019-03-25 | 7 | 0% | bar: WEEK 2 F; WEEK 4 M to WEEK 5 M
User must be able to view the results of a quiz, either directly after taking it OR viewing the results of a previously taken quiz. | Michael | 2019-03-25 | 2019-04-05 | 10 | 75% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
User must be able to access the raw data on cities as an index (City Index) | Andrew | 2019-03-25 | 2019-03-28 | 3 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 5 W
Application Requirements
Application must be able to store and modify user profile data | Nick | 2019-02-25 | 2019-03-11 | 16 | 50% | bar: WEEK 1 M to WEEK 1 F; WEEK 2 F to WEEK 3 M; WEEK 4 M to WEEK 4 F
Application must be able to store city data | Andrew | 2019-02-25 | 2019-03-11 | 16 | 100% | bar: WEEK 1 M to WEEK 3 M; WEEK 4 M to WEEK 4 F
Application must be able to take user quiz input and establish what city they would be most likely to enjoy living in | Michael | 2019-02-26 | 2019-03-22 | 26 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 F to WEEK 4 F
Application must be able to verify user credentials | Nick | 2019-03-11 | 2019-03-25 | 14 | 100% | bar: WEEK 2 F; WEEK 3 T to WEEK 5 M
Performance Attributes
System should respond to user’s input in less than 1 second. | Andrew | 2019-03-25 | 2019-04-01 | 6 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
System should be able to generate recommendations after survey completion in less than 30 seconds. | Michael | 2019-02-26 | 2019-03-22 | 26 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 F to WEEK 4 F
System should be able to support 1,000 simultaneous users. | Nick | 2019-03-29 | 2019-04-01 | 2 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 4 F; WEEK 5 F to WEEK 6 F
System should be able to survive a crash without loss of user data. | Andrew | 2019-03-28 | 2019-04-01 | 3 | 100% | bar: WEEK 2 F; WEEK 4 M to WEEK 4 F; WEEK 5 W to WEEK 6 F
Quality Attributes
The user’s info should be stored securely. | Michael | 2019-03-25 | 2019-04-05 | 10 | 25% | bar: WEEK 2 F; WEEK 4 M to WEEK 6 F
User should be able to complete survey and get recommended cities without creating a profile | Michael | 2019-02-26 | 2019-03-22 | 26 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 F to WEEK 4 F
Upon the user’s input of invalid credentials, system should prompt user to re-enter credentials on same page. | Nick | 2019-03-11 | 2019-03-19 | 8 | 50% | bar: WEEK 2 F; WEEK 3 T to WEEK 5 M
Website should not be down for more than 30 minutes per week. | Andrew | 2019-03-13 | 2019-03-20 | 7 | 0% | bar: WEEK 2 F; WEEK 3 T to WEEK 4 F
[6 empty] | 2019-02-25 |  |  |  |  | 2019-03-04 |  |  |  |  | 2019-03-11 |  |  |  |  | 2019-03-18 |  |  |  |  | 2019-03-25 |  |  |  |  | 2019-04-01
Spring Break